## teams
area | velocity | last update
infrastructure | 20 | 2019-10-12
bi | 50 | 2019-10-12
sm | 50 | 2019-10-12
integration | 70 | 2019-10-12
epsui | 23 | 2019-10-12

## infrastructure
ID | Title | Status | Tags | Story Points | Start | Duration | Percent
134672 | [Automation] Tableau pipeline adjustments for automation | Active | CSME MVP; Milestone C; Monkeys; NotReady | 5
127248 | [Automation]: Terraform network adjustments | Active | CB_APPROVED; CSME MVP; Milestone C; Monkeys; PI10; sprint 1 | 30
126794 | Automation of provisioning subscriptions: Config Adjustments (read/write), configuration design | Active | CB_APPROVED; CSME MVP; Milestone C; Monkeys | 30
135451 | DA adjustments - part 2 | Active | CSME MVP; Milestone C; Monkeys; PI10; sprint 2 | 5
136595 | Disaster Recovery Support and Integration | Active | Apes; Milestone F | 36 | 2019-10-02 | 90
135804 | EPS Adjustments | New | CSME MVP; Milestone C; Monkeys; Performance
106727 | Integration of SORTT SFTP Uploader into Release Pipeline | Active | CLE MVP; Milestone C; Monkeys; Pearl 15 Continuous; PI10; sprint 2 | 8
137200 | Migrate to feature branch delivery | New | Apes; Blocked; CSME MVP; Milestone C; PI10; sprint 1; Waiting for POC | 18
136603 | PenTesting security adjustments | New | Apes; Blocked; Milestone C; NothingToDoHere? | 2
135450 | Relation based deployment | New | Apes; CSME MVP; Milestone C; PI10; sprint 1 | 8
136564 | Release 1.2 support | Active | Milestone C; Monkeys | 13 |  | 20
137198 | Release in YAML PoC | Closed | Apes; CSME MVP; Milestone C; PI10 | 4
138286 | Release in YAML PoC - part 2 | Active | Apes; CSME MVP; Milestone C; PI10 | 1
137195 | Release Pipeline Support - Sprint 10.2 - Team Buzzard-Apes | Closed | Apes; CSME MVP; Milestone C; PI10; sprint 2 | 7 | 2019-10-16 | 14
137056 | Release Pipeline Support - Sprint 10.2 - Team Buzzard-Monkeys | Closed | Milestone C; Monkeys; PI10; sprint 2 | 8 | 2019-10-16 | 14
138199 | Release Pipeline Support - Sprint 10.3 - Team Buzzard-Apes | Active | Apes; CSME MVP; Milestone C; PI10; sprint 3 |  | 2019-10-30 | 14
138195 | Release Pipeline Support - Sprint 10.3 - Team Buzzard-Monkeys | New | Milestone C; Monkeys; PI10; sprint 3 |  | 2019-10-30 | 14
137199 | Security Compliance SP 10.2 | Closed | Apes; CSME MVP; Milestone C; PI10; Rework; sprint 2 | 11
138288 | Security Compliance SP 10.3 | Active | Apes; CSME MVP; Milestone C; PI10; Rework; sprint 3
136604 | Shared Services integration and lockdown Automation | New | Apes; Blocked; Milestone C; WaitingForFaisal
136171 | Splitting App service plan | Closed | Apes; CSME MVP; Milestone C; PI10; Waiting for MS discussion | 11
138221 | Splitting App service plan - part 2 after merge | Active | Apes; CSME MVP; Milestone C; PI10; Waiting for MS discussion | 2
69221 | Update "Continuous Integration & Delivery" LLD | New | CSME MVP; Fix2 | 8

## bi
ID | Title | Status | Tags | Story Points | Start | Duration | Percent
135457 | bi 1 | Closed | A | 0
137195 | bi 2 | Active | B | 8
132639 | bi 3 | Blocked | C | 22

## sm
ID | Title | Status | Tags | Story Points | Start | Duration | Percent
135457 | sm 1 | Closed | A | 0
137195 | sm2 | Active | B | 8
132639 | sm3 | Blocked | C | 20

## integration
ID | Title | Status | Tags | Story Points | Start | Duration | Percent
135457 | int3 | Closed | A | 0
137195 | int5 | Active | B | 8
132639 | ing6 | Blocked | C | 20

## epsui
ID | Title | Status | Tags | Story Points | Start | Duration | Percent
135457 | epsui 1 | Closed | A | 0
137195 | epsui 2 | Active | B | 8
132639 | epsui 3 | Blocked | C | 20

## Sheet1
ID | Title | Status | Tags | Story Points | Start | Duration | Percent