## teams
area | velocity | last update
infrastructure | 44 | 2020-01-12
bi | 50 | 2019-10-12
sm | 50 | 2019-10-12
integration | 70 | 2019-10-12
epsui | 23 | 2019-10-12

## infrastructure
ID | Title | Status | Tags | Story Points | Start | Duration | Percent | dependentOn | Area
143087 | YAML migrate pipelines - Apes | Active | Apes; Milestone C; Release 1.3; YAML | 7
143088 | YAML migrate pipelines - Monkeys | Active | Milestone C; Monkeys; Release 1.3; YAML | 6
143136 | YAML Scripts - Apes | Active | Apes; Milestone C; Release 1.3; YAML | 5 |  |  |  | 143087, 143088
142138 | Upgrade tableau autoamted deployment to use 2019.4 | Active | Milestone C; Release 1.3 | 5
143077 | Disaster Recovery Support and Integration | Active | Apes; Milestone D; Release 1.4 | 32 | 2020-01-07 | 84
143078 | Release Pipeline Support - Sprint 11.4 - Team Buzzard-Apes | Active | Apes; CSME MVP; Milestone C; PI11; Release 1.3 | 8 | 2020-01-07 | 14
143080 | Release Pipeline Support - Sprint 11.4 - Team Buzzard-Monkeys | Active | Milestone C; Monkeys; PI11; Release 1.3 | 7 | 2020-01-07 | 14
143148 | [Automation]: Network adjustments - testing | Active | CB_APPROVED; CSME MVP; Milestone C; Monkeys; PI11; Release 1.3; sprint 4 | 10
140669 | Onboarding Adam Jankowski | Active | Milestone C; Monkeys; Release 1.3 | 2
141665 | [F170] Databricks deploy | New | FTD_v1; Milestone E; Release 1.5; Review | 5
141924 | Hardcoded redirectURIs - domain EHM names | New | Milestone C; Monkeys; Release 1.3 | 5
142139 | Migration module release improvements for 1.3 | New | Milestone C; Release 1.3 | 10
142141 | Domain names EHM support | New | Milestone C; Release 1.3 | 5
142143 | Mergining with stg1,2 and mig3 branches | New | Milestone C; Release 1.3 | 8
142372 | Fix the issues with tagging | New | Apes; Milestone C; Release 1.3 | 5
138624 | Back up and Restore: DWH | New | Apes; Milestone C; PI11; Release 1.3; sprint 5 | 12
139426 | [Automation] Adjustments for scripts to use new config files - subscription 1 | New | Milestone C; Release 1.3 | 10
138472 | Release 1.3 pipeline adjustments and support | New | Milestone C; PI11; Release 1.3 | 13 | 2020-03-04 | 14
139428 | Automation of provisioning subscriptions: moving away from excel file | New | Milestone C; Monkeys; Release 1.3 | 8
140663 | Automation of provisioning subscriptions: configuration design - subscriptions - part 2 | New | CB_APPROVED; CSME MVP; Milestone C; Monkeys; PI11; Release 1.3; sprint 5 | 10
142434 | Security compliance IP11.2-5 buffer | New | Milestone C; Release 1.3 | 11
135450 | Relation based deployment | New | Apes; CSME MVP; Milestone C; PI11; Release 1.3; sprint 5 | 8
138621 | Back up and Restore: Cosmos DB | New | Apes; Milestone C; PI11; Release 1.3; sprint 4 | 8
142435 | Storing secrets in a proper way within repo | New | Milestone D | 1
142436 | Secret validation and Mapping of secrets | New | Milestone D | 1
142439 | Clean up of branches, RD, Task Groups etc. | New | Milestone D; Release 1.4 | 5
200001 | Release Pipeline Support - Sprint 11.5 - Team Buzzard-Apes | New | Apes; CSME MVP; Milestone C; PI11; Release 1.3 | 8 | 2020-01-21 | 14
200002 | Release Pipeline Support - Sprint 11.5 - Team Buzzard-Monkeys | New | Milestone C; Monkeys; PI11; Release 1.3 | 7 | 2020-01-21 | 14
200003 | Release Pipeline Support - Sprint 12.1 - Team Buzzard-Apes | New | Apes; CSME MVP; Milestone C; PI11; Release 1.3 | 8 | 2020-02-05 | 14
200004 | Release Pipeline Support - Sprint 12.1 - Team Buzzard-Monkeys | New | Milestone C; Monkeys; PI11; Release 1.3 | 7 | 2020-02-05 | 14
200005 | Release Pipeline Support - Sprint 12.2 - Team Buzzard-Apes | New | Apes; CSME MVP; Milestone C; PI11; Release 1.3 | 8 | 2020-02-19 | 14
200006 | Release Pipeline Support - Sprint 12.2- Team Buzzard-Monkeys | New | Milestone C; Monkeys; PI11; Release 1.3 | 7 | 2020-02-19 | 14
200007 | Release Pipeline Support - Sprint 12.3- Team Buzzard-Apes | New | Apes; CSME MVP; Milestone C; PI11; Release 1.3 | 8 | 2020-03-04 | 14
200008 | Release Pipeline Support - Sprint 12.3 - Team Buzzard-Monkeys | New | Milestone C; Monkeys; PI11; Release 1.3 | 7 | 2020-03-04 | 14
200009 | Release Pipeline Support - Sprint 12.4 - Team Buzzard-Apes | New | Apes; CSME MVP; Milestone C; PI11; Release 1.3 | 8 | 2020-03-18 | 14
200010 | Release Pipeline Support - Sprint 12.4 - Team Buzzard-Monkeys | New | Milestone C; Monkeys; PI11; Release 1.3 | 7 | 2020-03-18 | 14

## bi
ID | Title | Status | Tags | Story Points | Start | Duration | Percent
135457 | bi 1 | Closed | A | 0
137195 | bi 2 | Active | B | 8
132639 | bi 3 | Blocked | C | 22

## sm
ID | Title | Status | Tags | Story Points | Start | Duration | Percent
135457 | sm 1 | Closed | A | 0
137195 | sm2 | Active | B | 8
132639 | sm3 | Blocked | C | 20

## integration
ID | Title | Status | Tags | Story Points | Start | Duration | Percent
135457 | int3 | Closed | A | 0
137195 | int5 | Active | B | 8
132639 | ing6 | Blocked | C | 20

## epsui
ID | Title | Status | Tags | Story Points | Start | Duration | Percent
135457 | epsui 1 | Closed | A | 0
137195 | epsui 2 | Active | B | 8
132639 | epsui 3 | Blocked | C | 20

## Sheet1
ID | Title | Status | Tags | Story Points | Start | Duration | Percent